## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | COLLEGE FINDER INDIA |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID
PROJECT MANAGER
PROJECT SPONSOR
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 2025-06-20 | Gemini AI API response parsing failed during initial testing | Technical Implementation | API responses were inconsistent in structure, some test calls returned malformed JSON | Implement robust fallback mechanism with simpler prompts and comprehensive data validation before parsing | Created fallback system that tries simpler Gemini prompts if initial parsing fails | Abuzaid | COMPLETED | This issue led to improved error handling that made the final application more reliable
2 | 2025-06-25 | User interface design took longer than expected | Project Planning | Initial mockups were too complex for the timelin | Start with simpler UI designs and iterate based on user feedback | Redesigned with cleaner, simpler interface focusing on core functionality | Abuzaid | COMPLETED | Simple design actually improved user experience
3 | 2025-06-30 | College data accuracy varied by location | Data Quality | Some regions returned limited or outdated college information | Research and integrate multiple data sources for comprehensive coverage | Added data validation and fallback search mechanisms | Abuzaid | COMPLETED | Need to expand data sources for better coverage
4 | 2025-07-04 | Location input validation was initially overlooked | Requirements Analysis | No clear validation rules defined for location inputs during planning phase | Define input validation requirements early in project planning and create comprehensive test cases | Implemented location validation with error messages and auto-suggestions | Abuzaid | COMPLETED | Better user experience with clear error messages and suggestions
5 | 2025-07-10 | Deployment to Netlify required environment configuration adjustments | Deployment | & DevOpsBuild was successful locally but failed on deployment platform due to environment differences | Test deployment early in development cycle and document environment-specific configurations | Created deployment checklist and configured proper build settings for Netlify | Abuzaid | COMPLETED | Early deployment testing saves time and reduces last-minute issues